## Sheet1
Timetable of NAP - 1 Implementation
No | Activity | Implementing Agency | 2018 | [11 empty] | 2019
|  |  | Jan | Feb | Mar | Apr | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug
Rule of Law Working Group
1 | Establishing a committee who will be responsible for drafting the protection policy for women under conflict and emergency situations | MoWA | bar: 2018 Jan to 2018 Feb
2 | Preparing the draft plan for the joint committee to oversee the implementation of the Anti-Corruption Strategy | HOOAC | bar: 2018 Jan to 2018 Feb
3 | Drafting the amendments to LPPELD by MoJ | MoJ | bar: 2018 Jan to 2018 Feb
4 | Preparing a list of high-ranking officials whose assets are subject to registration and publication | HOOAC | bar: 2018 Jan to 2018 Mar
5 | Designing the organizational structure of special courts for VaW crimes in the 12 provinces based on the law by Supreme Court | Supreme Court | bar: 2018 Jan to 2018 July
6 | Holding two consultative meetings with related governmental agencies and CSOs on the draft amendments by MoJ | MoJ | bar: 2018 Mar to 2018 Apr
7 | Holding three consultative meetings with CSOs and relevant public departments to incorporate their inputs into the final draft plan | HOOAC | bar: 2018 Mar to 2018 May
8 | Drafting the protection policy for women under conflict and emergency situations by the committee | MoWA | bar: 2018 Mar to 2018 Aug
9 | Prioritizing registration of 100 officials’ assets and publicizing the list of 100 high-ranking officials via HOOAC website and media | HOOAC | bar: 2018 Apr to 2018 May
10 | Finalizing the amendments by Executive Committee of MoJ’s Legislation Department | MoJ | bar: 2018 May
11 | Presenting the finalized draft of the amendment to the legislative committee of Cabinet for its feedback | bar: 2018 June to 2018 July
12 | Presenting the final draft plan to the High Council on Rule of Law and Anti-Corruption for approval | HOOAC | bar: 2018 June to 2018 Aug
13 | Sending the assets forms to 100 high-ranking officials for completion and collection | bar: 2018 June to 2018 Oct
14 | Presenting the final amendments to the Cabinet for approval | MoJ | bar: 2018 Aug to 2018 Sep
15 | Holding 13 awareness raising sessions (one session in the center and 1 session in each of the 12 provinces) by the courts | Supreme Court | bar: 2018 Aug to 2019 Aug
16 | Establishing special courts for addressing VaW crimes in 12 provinces | bar: 2018 Aug to 2019 Aug
17 | Holding one consultation session in Kabul for finalizing the draft of the protection policy by the committee | MoWA | bar: 2018 Sep to 2018 Oct
18 | Establishment of the joint committee based on the approved plan by HOOAC | HOOAC | bar: 2018 Sep to 2018 Oct
19 | Approval of the amendments by the National Assembly | MoJ | bar: 2018 Oct to 2019 Mar
20 | Developing an action plan for the oversight of the implementation of the Anti-Corruption Strategy by joint committee | HOOAC | bar: 2018 Nov to 2018 Dec
21 | Establishing a mechanism for CSOs’ monitoring of the asset reviewing process jointly designed by HOOAC and CSOs | bar: 2018 Nov to 2018 Dec
22 | Publishing the registered assets of each of the 100 high-ranking officials as completed by HOOAC | bar: 2018 Nov to 2019 Jan
23 | Approval of the Protection Policy by the Cabinet | MoWA | bar: 2018 Nov to 2019 Feb
24 | Holding monthly meetings by the joint committee and providing reports to the High Council on Rule of Law and Anti-Corruption | HOOAC | bar: 2019 Jan to 2019 Aug
25 | Completing the reviewing of 100 officials’ assets with monitoring of CSOs based on established mechanism | bar: 2019 Feb to 2019 Aug
26 | Holding 5 public awareness raising campaigns on how to access HOOAC findings | bar: 2019 Mar to 2019 Aug
27 | Preparing and finalizing an action plan to facilitate the implementation of the policy by the committee | MoWA | bar: 2019 Mar to 2019 Aug
28 | Endorsing, publishing and enforcing the LPPELD | MoJ | bar: 2019 Apr to 2019 Aug
29 | Producing one knowledge product that highlights the challenges and lessons learnt for informing future anti-corruption strategies | HOOAC | bar: 2019 July to 2019 Aug
Governance and Financial Management Working Group
1 | Holding three joint meetings in order to revise, scrutinize and approve the mechanism of public partnership in the inspection process | HIO | bar: 2018 Jan to 2018 Mar
2 | Establishing the Information Units Reform Panel to develop a plan to inform the methodology of the assessment information units | MoIC | bar: 2018 Jan to 2018 Mar
3 | Establishment of essential administrative structures by High Inspection Office (HIO) | HIO | bar: 2018 Apr to 2018 Sep
4 | Assessment of 60 information units by IURP, producing and publicizing the findings of the assessment via MoIC website | MoIC | bar: 2018 Apr to 2018 Sep
5 | Holding two awareness-raising seminars on issues related to the CSOs and media participation in the inspection processes | HIO | bar: 2018 Oct to 2018 Dec
6 | Creating a capacity development program by IURP based on the findings of the assessment | MoIC | bar: 2018 Oct to 2019 Jan
7 | Formulating an Authorities Inspection Plan based on a risk assessment practice according to public partnership mechanism | HIO | bar: 2019 Jan to 2019 Mar
8 | Implementation of the capacity development program within the targeted ministries with the technical support of IURP | MoIC | bar: 2019 Feb to 2019 Aug
9 | Conduct 7 inspections based on the Authorities Inspection Plan | HIO | bar: 2019 Apr to 2019 Aug
10 | Producing a lessons learned report on the implementation of the program in the targeted ministries by IURP | MoIC | bar: 2019 May to 2019 Aug
Human Resources Development Working Group
1 | Drafting Health Service Accreditation Scheme by MoPH and publicizing the scheme via MoPH website | MoPH | bar: 2018 Jan to 2018 Feb
2 | Establishing a National Oversight Committee for the Transparency and Quality of Education and Higher Education with specific ToR | MoE & MoHE | bar: 2018 Jan to 2018 Feb
3 | Organizing two consultative sessions with relevant civil society organizations to finalize Health Service Accreditation Scheme | MoPH | bar: 2018 Mar to 2018 Apr
4 | Developing a holistic monitoring mechanism assessing the quality of teaching in education and higher education institutes by NOC | MoE & MoHE | bar: 2018 Mar to 2018 May
5 | Presenting the scheme to the cabinet for approval | MoPH | bar: 2018 May to 2018 June
6 | Presentation and approval of the aforesaid mechanism by MoE and MoHE | MoE & MoHE | bar: 2018 June to 2018 July
7 | Establish Health Service Accreditation Entity in Afghanistan | MoPH | bar: 2018 July to 2018 Dec
8 | Establishment of 4 subnational monitoring committees in Balk, Herat, Kandahar and Nangarhar by NOC | MoE & MoHE | bar: 2018 Aug to 2018 Oct
9 | Conducting Community Monitoring at the level of primary education in the capital of five provinces including Kabul | bar: 2018 Nov to 2019 June
10 | Conducting a student satisfaction survey at the level of higher education in 5 provinces, including Kabul | bar: 2018 Nov to 2019 June
11 | Registering and accrediting 20 health centers in the country based on the Health Service Accreditation Scheme | MoPH | bar: 2019 Jan to 2019 Aug
12 | Delivering 20 training courses to the staff of registered centers with Health Service Accreditation Entity | bar: 2019 Jan to 2019 Aug
13 | Publishing and disseminating 10000 pamphlets on the fundamental health service standards to the public | bar: 2019 Jan to 2019 Aug
14 | Initiating a survey to assess beneficiaries level of satisfaction and publishing the ranking list of the health centers | bar: 2019 Jan to 2019 Aug
15 | Publishing the findings of community monitoring and student satisfaction survey individually | MoE & MoHE | bar: 2019 July to 2019 Aug
Infrastructure Development Working Group
1 | Preparing the draft Urban Improvement and Rehabilitation National Policy | MUDH | bar: 2018 Jan to 2018 Feb
2 | Holding a consultative meeting with the social and civic organizations to attain their inputs on the draft of the policy | bar: 2018 Mar to 2018 May
3 | Holding two inter-ministerial consultative meetings to attain their inputs on the draft of the policy | bar: 2018 June to 2018 July
4 | Finalizing the policy and submiting it to High Council for Urban Development for the approval | bar: 2018 Aug to 2018 Dec
5 | Drafting an action plan for the implementation of the policy | bar: 2019 Jan to 2019 Feb
6 | Holding 2 consultative meetings with public sector departments and social and civic organizations on the draft action plan | bar: 2019 Mar to 2019 May
7 | Incorporating the comments and recommendations obtained from the consultations in preparing the final version of the action plan | bar: 2019 June to 2019 Aug
Peace, Security and Reintegration Working Group
1 | Establishing general directorates of community-based police (police mardumi) in 11 provinces of Afghanistan | MoI | bar: 2018 Jan to 2018 Dec
2 | Organizing 11 awareness conferences in 11 mentioned provinces, and holding councils’ elections | bar: 2018 Jan to 2018 Dec
3 | Holding 11 training programs on behalf of community-based police for the elected members of the councils in the 11 target provinces | bar: 2018 Jan to 2018 Dec
4 | Formulating and organizing monthly sessions for public-police partnership councils on their functions
5 | Publicizing the minutes of councils monthly sessions via MoI website